## Лист1
|  | M1 | M2 | M3 | M4 | M5 | M6 | M7
Task 1 | System Requirements | bar: M1
Task 2 | Technology research | bar: M1 to M2
Task 3 | UI Development | bar: M2 to M3
Task 4 | SSA Implementation | bar: M2 to M3
Task 5 | Firmware update | bar: M3 to M4
Task 6
Task 7 | Testings
Task 8 | Reportin
Task 9

## Sheet1
|  |  | M1 | M2 | M3 | M4 | M5 | M6 | M7
1 | System Requirements | M1 | bar: M1
2 | Proof of Concept | M1 | bar: M1
3 | Initial report | M1 | bar: M1
4 | Technology research | M2 | bar: M1 to M2
5 | Data sources research | M2 | bar: M1 to M2
6 | SSA Implementation | M3 | bar: M2 to M3
7 | UI Development | M4 | bar: M2 to M4
8 | Firmware update | M4 | bar: M3 to M4
9 | Intermediate report | M4 | bar: M4
10 | Fine-tuning | M6 | bar: M5 to M6
11 | Prototype validation and demonstration | M7 | bar: M6 to M7
12 | Final report | M7 | bar: M7